## intro
PROJECT - E COMMERCE WEB APPLICATION
s no | document name | testing type | team member | testing module | no of test cases | status | remarks
1 | defect report | manual testing | Priyanka V Kaviyanjali M Keerthana V S Asha R | Registration | 13 | done | N/A
2 |  |  |  | Login | 4 | done | N/A
3 |  |  |  | Contact us | 3 | done | N/A
4 |  |  |  | Test cases | 1 | done | N/A
5 |  |  |  | Cart | 3 | done | N/A
6 |  |  |  | Subscription | 1 | done | N/A
7 |  |  |  | product | 3 | done | N/A

## register_defect_report
DEFECT REPORT
S NO | Defect_id | Title/summary | Description | Module/features | Priority | Severity | Environment | Steps to reproduce | Expected result | Actual result | Proof | Reported by | Reported date | Assigned to | Status | Retest date | Remark
1 | Bug_reg_01 | Name field accepts numbers | The Name input field allows numeric characters, which should be restricted to alphabets only. | Registration | High | medium | SIT | 1. Navigate to Registration Page. 2. Enter numbers (e.g., "12345") in the Name field. 3. Submit form. | System should show validation error for invalid name. | System accepts numeric values in the Name field. |  | Priyanka | 2025-08-13 | Developer | New |  | Needs input validation
2 | Bug_reg_02 | Name field accepts special characters | The Name input field allows special characters (e.g., !, @, #), which should be restricted to alphabets only. | Registration | High | medium | SIT | 1. Navigate to Registration Page. 2. Enter special characters in the Name field. 3. Submit form. | System should show validation error for invalid name. | System accepts special characters in the Name field. |  | Priyanka | 2025-08-13 | Developer | New |  | Needs input validation
3 | Bug_reg_03 | Weak password validation | Password field accepts any characters (including . , ;) without restrictions, has no length requirement, no visibility toggle (eye icon), and no password strength indicator. | Registration | High | High | SIT | 1. Navigate to Enter Account Information page. 2. Type a password containing . , ; or fewer than 6 characters. 3. Click Submit. | Password should have character restrictions, minimum length (e.g., 6–8 chars), strength indicator, and visibility toggle. | Password accepts all characters and lengths; no validation, no indicator, no visibility toggle. |  | Priyanka | 2025-08-13 | Developer | New |  | Needs input validation
4 | Bug_reg_04 | Newsletter subscription not working | When selecting “Sign up for Newsletter” checkbox during account creation, no confirmation or welcome email is received. | Registration | High | medium | SIT | 1. Navigate to Enter Account Information page. 2. Check the “Sign up for Newsletter” box. 3. Complete registration. 4. Check inbox. | User should receive confirmation email/newsletter subscription success message. | No email received and no on-screen confirmation. |  | Priyanka | 2025-08-13 | Developer | New |  | Needs input validation
5 | Bug_reg_05 | Name fields accept invalid characters | First Name and Last Name fields accept numbers, special characters, and punctuation without validation. | Registration | medium | High | SIT | 1. Navigate to Address Information section. 2. Enter 1234@@!! in First Name or Last Name field. 3. Save changes. | Only alphabets should be allowed; validation error should appear for invalid inputs. | Field accepts any characters without validation. |  | Priyanka | 2025-08-13 | Developer | New |  | Needs input validation
6 | Bug_reg_06 | Address field accepts any format | Street address field accepts any format without checking if it meets guidelines (e.g., real address structure). | Registration | low | low | SIT | 1. Navigate to Address Information section. 2. Enter random characters or invalid address format. 3. Save changes. | Address should follow a structured format and reject nonsensical input. | Accepts any random characters without warning. |  | Priyanka | 2025-08-13 | Developer | New |  | Needs input validation
7 | Bug_reg_07 | Limited country options in dropdown | Country dropdown contains only limited country names, excluding many actual countries. | Registration | medium | High | SIT | 1. Navigate to Address Information section. 2. Open the country dropdown. 3. Search for missing countries (e.g., "Japan"). | Dropdown should list all recognized countries. | Many countries are missing from the list. |  | Priyanka | 2025-08-13 | Developer | New |  | Needs input validation
8 | Bug_reg_08 | State field accepts invalid input | State field allows numbers, special characters, and punctuation without validation. | Registration | medium | High | SIT | 1. Enter 123@@! in State field. 2. Save changes. | State should only accept alphabetic characters and spaces. | Field accepts any input without warning. |  | Priyanka | 2025-08-13 | Developer | New |  | Needs input validation
9 | Bug_reg_09 | City field accepts invalid input | City field allows numbers, special characters, and punctuation without validation. | Registration | medium | High | SIT | 1. Enter 987#@ in City field. 2. Save changes. | City should only accept alphabetic characters and spaces. | Field accepts any input without warning. |  | Priyanka | 2025-08-13 | Developer | New |  | Needs input validation
10 | Bug_reg_10 | Zipcode field accepts invalid input | Zipcode field accepts alphabets, special characters, and punctuation without validation. | Registration | high | High | SIT | 1. Enter AB@@123 in Zipcode field. 2. Save changes. | Zipcode should only accept valid numeric format based on country. | Field accepts any characters without warning. |  | Priyanka | 2025-08-13 | Developer | New |  | Needs input validation
11 | Bug_reg_11 | Mobile number field accepts invalid input | Mobile number field accepts alphabets, special characters, and punctuation, and has no country code option. | Registration | high | high | SIT | 1. Enter ABC@## in Mobile Number field. 2. Save changes. | Mobile number should only accept numeric values, validate length, and allow country code selection. | Field accepts any input without warning and no country code option. |  | Priyanka | 2025-08-13 | Developer | New |  | Needs input validation
12 | Bug_reg_12 | No confirmation dialog for Logout action | When clicking "Logout", the system logs the user out immediately without any confirmation prompt, which can cause accidental logouts. | Registration | medium | high | SIT | 1. Log in to the application. 2. Click Logout in the navigation menu. | System should display a confirmation dialog (e.g., “Are you sure you want to log out?”) before logging out. | User is logged out immediately without confirmation. |  | Priyanka | 2025-08-13 | Developer | New |  | Add confirmation dialog for Logout.
13 | Bug_reg_13 | No confirmation dialog for Delete Account action | When clicking "Delete Account", the account is deleted immediately without asking for user confirmation, which can cause permanent accidental deletion. | Registration | high | high | SIT | 1. Log in to the application. 2. Navigate to account settings. 3. Click Delete Account. | System should display a confirmation dialog (e.g., “Are you sure you want to delete your account? This action is irreversible.”) before proceeding. | Account is deleted immediately without confirmation. |  | Priyanka | 2025-08-13 | Developer | New |  | Add confirmation dialog for Delete Account.

## login_defect_report
Sl. No. | Defect ID | Title/Summary | Description | Modules/Features | Severity | Priority | Environment | Steps To Reproduce | Expected Result | Actual Result | Proof | Reported By | Reported Date | Assigned To | Status | Retest Date | Remark
1 | BUG_Login_001 | Input issues in subscription email field | To verify and validate the subscription icon with already existing subscibed email address on Signup/Login page | Login | Medium | Medium | SIT | Step 1: Click on the web application link Step 2: Open it on the google chrome search engine Step 3: Enter already existing subscribed email address on the email address text box Step 4: Click on subscribe icon/button | User should be not able to subscribe and pop up should arise as already existing email address | User is able to subscribe successfully |  | Priyanka V | 2025-08-13 | Developer 1 | New
2 | BUG_Login_002 | Name field accepts numbers | The Name input field allows numeric characters, which should be restricted to alphabets only. | Login | High | medium | SIT | 1. Navigate to Registration Page. 2. Enter numbers (e.g., "12345") in the Name field. 3. Submit form. | System should show validation error for invalid name. | System accepts numeric values in the Name field. |  | Priyanka V | 2025-08-13 | Developer 1 | New
3 | BUG_Login_003 | Name field accepts special characters | The Name input field allows special characters (e.g., !, @, #), which should be restricted to alphabets only. | Login | High | medium | SIT | 1. Navigate to Registration Page. 2. Enter special characters in the Name field. 3. Submit form. | System should show validation error for invalid name. | System accepts special characters in the Name field. |  | Priyanka V | 2025-08-13 | Developer 1 | New
4 | BUG_Login_004 | Weak password validation | Password field accepts any characters (including . , ;) without restrictions, has no length requirement, no visibility toggle (eye icon), and no password strength indicator. | Login | High | High | SIT | 1. Navigate to Enter Account Information page. 2. Type a password containing . , ; or fewer than 6 characters. 3. Click Submit. | Password should have character restrictions, minimum length (e.g., 6–8 chars), strength indicator, and visibility toggle. | Password accepts all characters and lengths; no validation, no indicator, no visibility toggle. |  | Priyanka V | 2025-08-13 | Developer | New

## contactus_defect_report
Sl. No. | Defect ID | Title/Summary | Description | Modules/Features | Severity | Priority | Environment | Steps To Reproduce | Expected Result | Actual Result | Reported By | Reported Date | Assigned To | Status | Retest Date | Remark
1 | BUG_Contact_Us_001 | Input issues in name field | To verify and validate the name text box and give invalid name on the contact us page | Contact Us | High | High | SIT | Step 1: Click on the web application link Step 2: Open it on the browser Step 3: Check on get in touch section Step 4: Click on the name text box and give valid name | User should be not able to submit the response | User is able to submit the response | Priyanka V | 2025-08-13 | Developer 1 | New
2 | BUG_Contact_Us_002 | Input issues in message field | To verify and validate the message text box on get in touch section is submitted without any data on the contact us page | Contact Us | Low | Low | SIT | Step 1: Click on the web application link Step 2: Open it on the google chrome search engine Step 3: Check on get in touch section Step 4: Click on the message text box and give no data | User should be not able to submit the response | User is able to submit the response | Priyanka V | 2025-08-13 | Developer 1 | New
3 | BUG_Contact_Us_003 | Input issues in subscription email field | To verify and validate the subscription icon with already existing subscibed email address on contact us page | Contact Us | Medium | Medium | SIT | Step 1: Click on the web application link Step 2: Open it on the browser Step 3: Enter already existing subscribed email address on the email address text box Step 4: Click on subscribe icon/button | User should be not able to subscribe and pop up should arise as already existing email address | User is able to subscribe successfully | Priyanka V | 2025-08-13 | Developer 1 | New

## testcases_defect_report
Sl. No. | Defect ID | Title/Summary | Description | Modules/Features | Severity | Priority | Environment | Steps To Reproduce | Expected Result | Actual Result | Reported By | Reported Date | Assigned To | Status | Retest Date | Remark
1 | BUG_Test_Cases_001 | Input issues in subscription email field | To verify and validate the subscription icon with already existing subscibed email address on test cases page | Test Cases | Medium | Medium | SIT | Step 1: Click on the web application link Step 2: Open it on the browser Step 3: Enter already existing subscribed email address on the email address text box Step 4: Click on subscribe icon/button | User should be not able to subscribe and pop up should arise as already existing email address | User is able to subscribe successfully | Priyanka V | 2025-08-13 | Developer 1 | New

## cart_defect_report
Sl. No. | Defect ID | Title/Summary | Description | Modules/Features | Severity | Priority | Environment | Steps To Reproduce | Expected Result | Actual Result | Reported By | Reported Date | Assigned To | Status | Retest Date | Remark
1 | BUG_Cart_001 | Input issues in subscription email field | To verify and validate the subscription icon with already existing subscibed email address on cart page | Cart | Medium | Medium | SIT | Step 1: Click on the web application link Step 2: Open it on the browser Step 3: Enter already existing subscribed email address on the email address text box Step 4: Click on subscribe icon/button | User should be not able to subscribe and pop up should arise as already existing email address | User is able to subscribe successfully | Priyanka V | 2025-08-13 | Developer 1 | New

## product_defect_report
Sl. No. | Defect ID | Title/Summary | Description | Modules/Features | Severity | Priority | Environment | Steps To Reproduce | Expected Result | Actual Result | Reported By | Reported Date | Assigned To | Status | Retest Date | Remark
1 | BUG_Products_001 | Input issues in subscription email field | To verify and validate the subscription icon with already existing subscibed email address on product page | Products | Medium | Medium | SIT | Step 1: Click on the web application link Step 2: Open it on the browser Step 3: Enter already existing subscribed email address on the email address text box Step 4: Click on subscribe icon/button | User should be not able to subscribe and pop up should arise as already existing email address | User is able to subscribe successfully | Priyanka V | 2025-08-13 | Developer 1 | New
2 | BUG_Products_002 | Input issues in quantity of the product field | To verify and validate to enter number with invalid range in quantity input field text box on the product page | Products | High | High | SIT | Step 1: Click on the web application link Step 2: Open it on the browser Step 3: Click on the Product icon in home page Step 4: Check 'ALL PRODUCTS' is visible Step 5: Click on the 'View Product' Step 6: Click on the quantity input field text box and enter number with invalid range | User should be not able to enter number with invalid range in quantity input field text box | User is able to enter number with invalid range in quantity input field text box | Priyanka V | 2025-08-13 | Developer 1 | New
3 | BUG_Products_003 | Input issues in name field | To verify and validate 'WRITE YOUR REVIEW' section has your name text box fill with invalid name on the product page | Products | Medium | Medium | SIT | Step 1: Click on the web application link Step 2: Open it on the browser Step 3: Click on the Product icon in home page Step 4: On 'View Product' in 'WRITE YOUR REVIEW' section has your name text box fill with invalid name | User should be not able to submit the review and pop up should arise as no numbers or special characters | User is able to submit the review | Priyanka V | 2025-08-13 | Developer 1 | New

## sub_defect_report
Sl. No. | Defect ID | Title/Summary | Description | Modules/Features | Severity | Priority | Environment | Steps To Reproduce | Expected Result | Actual Result | Reported By | Reported Date | Assigned To | Status | Retest Date | Remark
1 | BUG_Sub_Home_001 | Input issues in subscription email field | To verify and validate the subscription icon with already existing subscibed email address on home page | Subscription Home | Medium | Medium | SIT | Step 1: Click on the web application link Step 2: Open it on the google chrome search engine Step 3: Enter already existing subscribed email address on the email address text box Step 4: Click on subscribe icon/button | User should be not able to subscribe and pop up should arise as already existing email address | User is able to subscribe successfully | Priyanka V | 2025-08-13 | Developer 1 | New